## planning
Infovis global wind power exploration |  |  | 0 | 0 | 2024-05-19 | 2024-02-01 | 2
 | time axis 2024-01-29 to 2024-09-22
Task | Who | Start | End | Duration | %Complete |  | 2024-01-29: 2024-01-29; 2024-02-05: 2024-02-05; 2024-02-12: 2024-02-12; 2024-02-19: 2024-02-19; 2024-02-26: 2024-02-26; 2024-03-04: 2024-03-04; 2024-03-11: 2024-03-11; 2024-03-18: 2024-03-18; 2024-03-25: 2024-03-25; 2024-04-01: 2024-04-01; 2024-04-08: 2024-04-08; 2024-04-15: 2024-04-15; 2024-04-22: 2024-04-22; 2024-04-29: 2024-04-29; 2024-05-06: 2024-05-06; 2024-05-13: 2024-05-13; 2024-05-20: 2024-05-20; 2024-05-27: 2024-05-27; 2024-06-03: 2024-06-03; 2024-06-10: 2024-06-10; 2024-06-17: 2024-06-17; 2024-06-24: 2024-06-24; 2024-07-01: 2024-07-01; 2024-07-08: 2024-07-08; 2024-07-15: 2024-07-15; 2024-07-22: 2024-07-22; 2024-07-29: 2024-07-29; 2024-08-05: 2024-08-05; 2024-08-12: 2024-08-12; 2024-08-19: 2024-08-19; 2024-08-26: 2024-08-26; 2024-09-02: 2024-09-02; 2024-09-09: 2024-09-09; 2024-09-16: 2024-09-16
Taken |  | 2024-02-20 | 2024-05-26 | 97 | 100%
clinic: intro project | J+M | 2024-02-20 | 2024-02-20 | 1 | 100%
team call: debrief clinic | J+M+R | 2024-02-21 | 2024-02-21 | 1 | 100%
setting up team collab channels (github, whatsapp) | J | 2024-02-22 | 2024-02-22 | 1 | 100%
setting up dash example code | J+M | 2024-03-12 | 2024-03-12 | 1 | 100%
team call: dataset discussion | J+M+R | 2024-02-26 | 2024-02-26 | 1 | 100%
drafting dataset doc | J | 2024-02-26 | 2024-02-29 | 4 | 100%
review dataset doc | M+R | 2024-02-29 | 2024-03-03 | 4 | 100%
dataset doc submission | J | 2024-03-03 | 2024-03-03 | 1 | 100%
data preprocessing + eda notebook | J | 2024-03-17 | 2024-03-18 | 2 | 100%
team call: data validation | J+M+R | 2024-04-02 | 2024-04-02 | 1 | 100%
prepare interim presentation | J | 2024-04-02 | 2024-04-08 | 7 | 100%
review interim presentation | M+R | 2024-04-08 | 2024-04-14 | 7 | 100%
team call: prepare interim presentation | J+M+R | 2024-04-16 | 2024-04-16 | 1 | 100%
online interim presentation | J+M+R | 2024-04-18 | 2024-04-18 | 1 | 100%
unavailable (abroad) | J | 2024-04-21 | 2024-04-25 | 5 | 100%
unavailable (abroad) | R | 2024-04-21 | 2024-04-25 | 5 | 100%
clinic: interim presentations | J+M+R | 2024-04-23 | 2024-04-23 | 1 | 100%
sprint 1: data processing / aggregation / filters / interactivity | J | 2024-04-22 | 2024-05-05 | 14 | 100%
sprint 1: bar charts, BAN, popups | M | 2024-04-22 | 2024-05-05 | 14 | 100%
sprint 1: map plot (framework selection, notebook impl) | R | 2024-04-22 | 2024-05-05 | 14 | 100%
team call: sprint review | J+M+R | 2024-05-09 | 2024-05-09 | 1 | 100%
sprint 2: cross validation + tweaking + bugfixing | J | 2024-05-06 | 2024-05-19 | 14 | 100%
sprint 2: cross validation + tweaking + bugfixing | M | 2024-05-06 | 2024-05-19 | 14 | 100%
sprint 2: cross validation + tweaking + bugfixing | R | 2024-05-06 | 2024-05-19 | 14 | 100%
unavailable (abroad) | J | 2024-05-12 | 2024-05-17 | 6 | 100%
team call: sprint review + final actions | J+M+R | 2024-05-19 | 2024-05-19 | 1 | 100%
final ppt + report drafting | J | 2024-05-20 | 2024-05-24 | 5 | 0%
final ppt + report drafting | M | 2024-05-20 | 2024-05-24 | 5 | 0%
final ppt + report drafting | R | 2024-05-20 | 2024-05-24 | 5 | 0%
final project presentation | J+M+R | 2024-05-23 | 2024-05-23 | 1 | 0%
deadline final report | J+M+R | 2024-05-26 | 2024-05-26 | 1 | 0%
Note on C3: Start Date Enter the starting date for this task. To associate the start date with the end of another task, enter a formula in the start date that refers to the end date of that task.
Note on D3: End Date The ending date is calculated by adding the Duration (calendar days) to the Start date minus 1 day, because the task duration is from the beginning of the Start day to the end of the End day.
Note on E3: Duration (Calendar Days) Enter the number of calendar days for the given task. Refer to the Working Days column or use a calendar to determine the corresponding working days. The duration is from the beginning of the Start date to the ending of the End Date. When the duration is calculated, it is calculated as End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day.
Note on F3: Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%).
Note on G3: Working Days Counts the number of working days using the NETWORKDAYS() formula, which excludes weekends. When planning work based upon the number of working days, adjust the Duration until the desired # of working days is reached.
Note on H3: Calendar Days Complete This column is calculated by multiplying the Duration by the %Complete and rounding down to the nearest integer.
Note on I3: Calendar Days Remaining This column is calculated by subtracting the Days Complete from the Duration.

## uitleg
project startdatum invullen in G1
als je visualisatie wil offsetten per week - dat bedrag invullen in E1